## Sheet1
TPN Audit requirements - Decision on feasibility of the below mentioned action items
Sno | Requirements | Feasibility | Time Frame | Responsibility
General Security Policies
1 | LDAP server (domain) – requires a backup domain physically present | Mandatory | Done | -
2 | Password Policy to be setup only for 30 days instead of 90 days | Required | Done | -
3 | Password length (8-14) required user to have 12 character/admin to have 15 characters, servers admin 16 characters | Mandatory | Done | Mangesh/Aquib
4 | Admin user to be additionally added, no ROOT account to be used for workstations and server | Mandatory | Done | Mangesh/Aquib
5 | Check for internet on workstation (Internet not-available on Artist workstations – Non-production have Internet on their systems on non-production VLAN, treated as exception) | Exception | - | -
6 | PORT 22 for SFTP to enabled - allow PORT 22 on Firewall and disable PORT 21 (Need to discuss) | Mandatory | Done | Mangesh/Aquib
7 | Set Screen Saver 5 minutes only (cannot be changed as NoMachine/Teradici times-out due to this) | Exception | -
8 | USB charging from workstations to be disabled (need to identify Hardware settings for the same) | Mandatory | Need to check | Mangesh/Sam
9 | Patch Management to be setup – Mandatory patch upgrade every week (currently being done using REPO server, however O/S and dependency files are only updated, CENTOS version upgrades automatically incorporate security patches) | Mandatory | Done | -
10 | Downtime to be restricted to 72 hours only (Never exceeded 72 hours downtime so far) – Incident Management Report to be updated with last electricity failure | Mandatory | 1 day | Seema
Local Network Security Requirements
11 | No internet for IT team (should be treated as exception as IT engineers need Internet access for Remote access management of Artist Systems) | Exception | - | -
12 | No PING allowed on internal systems (will be disabled during audit) | Mandatory | Script will run on audit day | Mangesh/Aquib
13 | Empty PORTS to be disabled on the switches | Mandatory | Done | -
Firewall Security Requirements
14 | Remove all Whitelisting of web sites from Firewall, reassign only allowed web sites | Mandatory | DOne/Except aspera and syncthing | Mangesh
15 | IDS/IPS mandatory (IPS already configured on Sophos F/W, IDS to be confirmed on Antivirus) | Mandatory | IPS already done.need to cehck with IDS | Mangesh/Aquib
16 | F/W logs are sent regularly (monthly) Keep weekly (was done earlier, will be incorporated from today) | Mandatory | Done | Mangesh/Aquib
17 | SYSLOG Server is mandatory (Log Server) - Systems/workstations LOG (will need to setup SYSLOG Server and make it operational for collecting logs for Firewall/Storage/Network devices) | Mandatory | Done | Mangesh/Aquib
18 | oPManager (Bandwidth Manager/System Utilization) – Time stamp/source location/user info/content in use (need to discuss further – look for open source alternatives) | Mandatory | Done/we are using cacti | Mangesh/Sam
Server Room & Facility Security Requirements
19 | Require a nominated IT Security staff (Sam is nominated CISO for ISO27001 and continues this role) | Mandatory | Done | -
20 | Data I/O staff especially for file transfers and HDD data copies (No Data Ops in company, Data Ops activity is taken care of Production based on Projects. Transfer of data to HDDs happens with IT under authorization from Production) | Exception | - | -
21 | Keep details of Firmware of F/W & Switches/Storage – (Documentation to be maintained and shared during audit) | Mandatory | Done | Mangesh/Aquib
22 | Keep Server details ready – (Documentation to be maintained and shared during audit) | Mandatory | Done | Mangesh/Aquib
23 | Keep Storage details ready – (Documentation to be maintained and shared during audit) | Mandatory | Done | Mangesh/Aquib
24 | CCTV required in Server Rooms | Mandatory | Done | -
25 | Motion detection lights in server room | Exception | - | -
26 | Server-room door alarm (to be available on both server room) – timer of 5 minutes | Exception | - | -
27 | Monitor with CCTV screen to be setup at security guard. With recording up to 90 days (need to provision with a system+monitor at the security desk - can provision Aniket's system temporary) | Mandatory | Done | Mangesh/Kade/Seema
28 | Mobile phone usage in premises – provide a list of IT, with Camera/without Camera, align with Mobile usage policy (there is an existing Mobile Usage Policy which caters to usage on premises) | Exception | - | -
29 | Grievance box to be placed not visible to the Camera | Exception | - | -
30 | Internal Mail Server should not be Pingable (disable internal PING to mail server during Audit) | Mandatory | - | Mangesh/Aquib
31 | HDDs with password protection & encryption required when sending out of the Studio (256 bit encryption required) - (Sam to check if the questionnaire if Vaults have mentioned) | Exception | 1 day | Sam
32 | WiFi SSIDs should not contain company name as its identification (in progress) | Mandatory | Done | Mangesh/Aquib
33 | ID card should not contain original name of the Artist, secondly only Photograph with a Pseudo name allowed (cannot be changed) - refer to HR Policy | Exception | - | -
34 | Temp guest user and password for WiFi with limited access only with duration based access only (Since we have Un-Managed WIFI device there is no possibility of creating rules for temp Wifi users hence then need to maintain a Register and note details of WIFI routers resets regularly – Need to also add in the INFOSEC policy) | Mandatory | Device is not negotaiable for mention requirement | Sam/Seema
35 | Godrej Safe (136Kgs) to be retained for HDDs both client as well as Assemblage to be treated as Vault & Fire proof safe (As we do not maintain HDDs of clients, there is no need for Vault/Safe) | Exception | - | -
36 | BCP/DR – Backup data to be retained other than premises (Need to discuss with Arjun & Close) | Mandatory | 2 days | Arjun/Priyank/Sam
37 | Will require Floor Layout & Network diagram (Digital copties will be maintained) | Mandatory | Done | Mangesh/Seema/Aniket
38 | Need to keep all CPUs of workstations under lock and key and keys are maintained by IT/Security (Seema to confirm systems with lock and keys) | Mandatory | Done | Seema/Mangesh